## Instructions
		Using the Status tracker

At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
	If 5 team members each spent an hour, that counts as 5 hours
	Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)

For new activities, identify the type of activity - documentation, coordination, estimation etc.

At the end of each week, plan ahead for the following week
	Identify people responsible for each activity
	Estimate the hours needed for the activity

TEAM NAME	Team 38
PROJECT NAME	Arithmetic Animator
PROJECT MENTOR	Dr. Sudhakar Pattagunta, Dr. Suresh Purini
TEAM MEMBERS	Arnav Sharma
	Sai Praneeth
	Somay Jain
	Sri Harsha

## Team_Status
TEAM NAME	Team 38
PROJECT NAME	Arithmetic Animator
PROJECT MENTOR	Dr. Sudhakar Pattagunta, Dr. Suresh Purini

Activity Name	Type	Responsible	Estimated Team Hours	Actual Hours	Status	Comments	Estimation error	Estimation error %
See Instructions sheet for usage
Week 6 (sept 5- sept 11)
Role preferences	Coordination	Sai Praneeth	1	0.5	Ongoing		0.5	100
Meeting with Project Mentor	Requirements	Arnav	2	2	Done		0	0
Decide on technology to be used	Requirements	Somay	1	2	Done		-1	50
Project synopsis writeup	Documentation	Arnav	1	1	Done		0	0
Team Meeting	Coordination	Sri Harsha	1	1	Done		0	0
Status tracker	Documentation	Somay	0.5	0.3	Done		0.2	66.6666666667
Week 7 (sept 12 - sept 18)
Learn Javascript	Preparation	Sri Harsha, Sai Praneeth	6	6	Planned	Learn Syntax	0	0
Make a elementary app using animations(2)	Development	Sri Harsha, Sai Praneeth	12	10	Planned	Using Javascript. Aim : Comfort with Javascript
Learn HTML5, CSS3	Preparation	Arnav, Somay	6	6	Planned	Learn Syntax
Make a elementary app using animations(1)	Development	Somay, Arnav	12	10	Planned	Using HTML5 Canvas. Aim : Comfort with HTML5
Role Preferences	Coordination	Sai Praneeth	0.5	1	Done		-0.5	50
Study Capability of PhoneGap/Titanium	Requirements	Arnav	3	4	Done		-1	25
Project Plan	Documentation	Somay	4	5	Done	Decide Project Modules(Abstractions) to be implementerd	-1	20
SVN Repository setup	Preparation	Sri Harsha	1		Planned
UI Design	Design	Arnav, Somay	1	1	Done	Sketching on Paper	0	0
Week 8 (sept 19 - sept 25)
Learn Javascript	Preparation	Sri Harsha, Sai Praneeth	6	4	Ongoing	Learn Syntax (Phase 2)	2	50
Make a elementary app using animations(2)	Development	Sri Harsha, Sai Praneeth	12	9		Using Javascript. Aim : Comfort with Javascript (Phase2)	3	33.3333333333
Learn HTML5, CSS3	Preparation	Arnav, Somay	6	8	Done	Learn Syntax (Phase2)	-2	25
Make a elementary app using animations(1)	Development	Somay, Arnav	12	14	Done	Using HTML5 Canvas. Aim : Comfort with HTML5 (Phase2)	-2	14.2857142857
Start Towards Actual Product Development	Development	Somay, Arnav, Harsha, Sai Praneeth	6	4	Done
Week 10(sept 26- oct 2)
SRS	Documentation	Arnav, Sri Harsha	5	6			-1	16.6666666667
Make the Illustration Page using Animated Objects	Development	Somay	6	10	Ongoing		-4	40
Finalise UI Designs	Design	Arnav	5	3
Make the Welcome Page	Development	Sri Harsha, Sai Praneeth	5	5	Done		0	0
Week 12(oct 3 – oct 9)
Make the Illustration Page using Animated Objects	Development	Somay	6	8	Done		-2	25
Add Instructions to Illustration Page	Development	Sri Harsha, Sai Praneeth	4		Ongoing
Make application prototype for iOS	Development	Somay	1	1	Done
Make the application prototype for Android	Development	Arnav	1	1	Done
Make a Input Fetching Page for Illustration	Development	Arnav	5		Ongoing
Week 13(oct 10 – oct 16)
Design Document	Documentation	Sri Harsha, Sai Praneeth	5	7	Done		-2	28.5714285714
Test Plan	Documentation	Somay	3	3	Done		0	0
Make a Uniform Design using CSS for all pages	Development	Somay, Arnav	5	6	Done		-1	16.6666666667
Make a Input Fetching Page for Illustration	Development	Arnav	5	6	Done		-1	16.6666666667
Add Instructions to Illustration Page	Development	Somay	4	5	Done
Make a Logo for App Page	Design	Sri Harsha	3	4	Done
Make presentation	Documentation	Sai Praneeth	3	4	Done
Meeting with Project Mentor	Preparation	Sai Praneeth, Sri Harsha	2	2	Done
Add Highlighting to Illustration Page	Development	Somay, Sai Praneeth	2	1	Done		1	100
Week 14

Week 15

Week 16

Week 17

## Individual_Status
TEAM NAME	Team 38
PROJECT NAME	Arithmetic Animator
PROJECT MENTOR	Dr. Sudhakar Pattagunta, Dr. Suresh Purini

Actvities	Arnav Sharma		Sai Praneeth		Somay Jain		Sri Harsha		0		Estimated Total Hours	Actual Total Hours
	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent
Week 6 (sept 5- sept 11)
Role preferences	0	0	1	0.5	0	0	0	0			1	0.5
Meeting with Project Mentor	0.5	0.5	0.5	0.5	0.5	0.5	0.5	0.5			2	2
Decide on technology to be used	0.5	0.5	0	0	0.5	1.5	0	0			1	2
Project synopsis writeup	1	1	0	0	0	0	0	0			1	1
Team Meeting	0.25	0.25	0.25	0.25	0.25	0.25	0.25	0.25			1	1
Status tracker	0	0	0	0	0.5	0.3	0	0			0.5	0.3
Week 7 (sept 12 - sept 18)
Learn Javascript	1.5		1.5		1.5		1.5				6	0
Make a elementary app using animations(2)	0		6		0		6				12	0
Learn HTML5, CSS3	1.5		1.5		1.5		1.5				6	0
Make a elementary app using animations(1)	6		0		6		0				12	0
Role Preferences	0		0		0		0.5				0.5	0
Study Capability of PhoneGap/Titanium	3		0		0		0				3
Project Plan	0.5		1		1.5		1				4
SVN Repository setup	0		0		0		1				1
UI Design	0.5		0		0.5		0				1	0
Week 8 (sept 19 - sept 25)
Learn Javascript						0	0
Make a elementary app using animations(2)						0	0
Learn HTML5, CSS3						0	0
Make a elementary app using animations(1)						0	0
Start Towards Actual Product Development						0	0
Week 10(sept 26- oct 2)						0	0
SRS						0	0
Make the Illustration Page using Animated Objects						0	0
Finalise UI Designs						0	0
Make the Welcome Page						0	0
Week 12(oct 3 – oct 9)						0	0
#NAME?						0	0
Make the Illustration Page using Animated Objects						0	0
Add Instructions to Illustration Page						0	0
Make the application prototype for Android						0	0
Make a Input Fetching Page for Illustration						0	0
Week 13(oct 10 – oct 16)						0	0
Design Document						0	0
Test Plan						0	0
Make a Uniform Design using CSS for all pages						0	0
#NAME?						0	0
0						0	0
0						0	0
0						0	0
0						0	0
Week 15						0	0
0						0	0
0						0	0
0						0	0
Week 16						0	0
0						0	0
0						0	0
0						0	0
0						0	0
Week 17						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0